## Project Plan
| Special Events |  | Start | End |  | Project Plan Template
| Overseas Leave |  | 2012-07-22 | 2012-07-25
[6 empty] | 2012-05-28 |  |  |  | 2012-06-01 | [20 empty] | 2012-07-02 | [21 empty] | 2012-08-01 | [22 empty] | 2012-09-03
 | time axis 2012-05-28 to 2012-09-28
|  |  | Start | End | % Compl.
Requirement Analysis |  |  | 2012-06-18 | 2012-07-13
Analysis of BOTLAID file |  |  |  |  | 80% | bar: 2012-07-23 to 2012-07-25
| Pattern matching |  | 2012-06-27 | 2012-07-02 | 60% | bar: 2012-07-23 to 2012-07-25
| Parsing of BOTLAID |  | 2012-07-03 | 2012-07-10 | bar: 2012-07-23 to 2012-07-25
| Testing & debugging |  | 2012-07-10 | 2012-07-13 | bar: 2012-07-23 to 2012-07-25
Parsing of Text file |  |  | 2012-06-18 | 2012-06-20 | bar: 2012-06-18 to 2012-06-20; 2012-07-23 to 2012-07-25
| Testing & debugging |  | 2012-06-20 | 2012-06-20 | bar: 2012-06-20; 2012-07-23 to 2012-07-25
Version 0.1 |  |  | 2012-06-21 | 2012-07-04 | 10% | bar: 2012-06-21 to 2012-07-04; 2012-07-23 to 2012-07-25
Product 1.0 |  |  | #REF! | #REF!
Version 0.2 |  |  | 2012-07-05 | 2012-07-17 | 25% | bar: 2012-07-05 to 2012-07-11; 2012-07-23 to 2012-07-25
| Testing & debugging |  | 2012-07-17 | 2012-07-19 | bar: 2012-07-11 to 2012-07-13; 2012-07-23 to 2012-07-25
Version 0.3 |  |  | 2012-07-20 | 2012-07-25 | 40% | bar: 2012-07-16 to 2012-07-25
| Testing & debugging |  | 2012-07-26 | 2012-07-30 | bar: 2012-07-23 to 2012-07-30
Version 0.4 |  |  | 2012-07-31 | #REF! | bar: 2012-07-23 to 2012-07-25; 2012-07-31 to 2012-08-06
| Testing & debugging |  | #REF! | #REF! | bar: 2012-07-23 to 2012-07-25; 2012-08-07 to 2012-08-08
|  | Version 1.0 | #REF! | #REF! | 0% | bar: 2012-07-23 to 2012-07-25
Project 2.0 |  |  | #REF! | #REF!
| Analysis of System 6 |  | #REF! | #REF! | 0%
| Pattern Matching of System 6 |  | #REF! | #REF! | 0%
| Version 2.0 |  | #REF! | #REF! | 0%
Project Deliverable 4 |  |  | #REF! | #REF!
| Task 1 |  | #REF! | #REF! | 0%
|  | Sub Task 1 | #REF! | #REF! | 0%
| Task 2 |  | 2010-05-10 | 2010-05-30 | 0%
| Task 3 |  | 2010-05-31 | 2010-06-20 | 0%
| Task 4 |  | 2010-06-13 | 2010-07-04 | 0%
Project Deliverable 5 |  |  | 2010-07-05 | 2010-08-15
| Task 1 |  | 2010-07-05 | 2010-07-18 | 0%
| Task 2 |  | 2010-07-19 | 2010-08-01 | 0%
| Task 3 |  | 2010-08-02 | 2010-08-08 | 0%
| Task 4 |  | 2010-08-09 | 2010-08-15 | 0%
Formulas:
Start = MIN([Start, row below]:D18)
Start = [End, row above]+1
End = MAX([End, row below]:E18)
End = [Start]+5+CHOOSE(WEEKDAY([Start]+5,2),0,0,0,0,0,2,1)

## Versioning
Version Number | Task Description/ Change Log | Number of Days Estimated | Estimated Date of completion | Actual Days taken | Actual Date of Completion
- | Parsing of BOTLAIDS | 8 | 2012-06-20 06:51 | 11 | 2012-06-21
- | Creating Data Template | 5 | 2012-06-26 17:09 | 6 | 2012-06-27
- | Integration of BOTLAID and Sample Data | 7 | 2012-07-05 17:09
1.0 | Include UI, system integration, finalise Data template | 7 | 2012-07-16 17:09
1.1 | Able to take in multiple BOTLAIDS (back end) | 5 | 2012-07-23 03:26
1.2 | Integration of BOTLAID and Sample Data | 5 | 2012-07-30 13:43
2.0 | Able to read multiple campagin in 1 excel file, change in UI to select multiple BOTLAID | 5 | 2012-08-06
Formulas:
Estimated Date of completion = (DATE(2012,6,10)+[Number of Days Estimated]+[Number of Days Estimated]/7*2)+IF(WEEKDAY((DATE(2012,6,10)+[Number of Days Estimated]+[Number of Days Estimated]/7*2),2)=6,2,0)+IF(WEEKDAY((DATE(2012,6,10)+[Number of Days Estimated]+[Number of Days Estimated]/7*2),2)=7,1,0)
Estimated Date of completion = ([Estimated Date of completion, row above]+[Number of Days Estimated]+[Number of Days Estimated]/7*2)+IF(WEEKDAY(([Estimated Date of completion, row above]+[Number of Days Estimated]+[Number of Days Estimated]/7*2),2)=6,2,0)+IF(WEEKDAY(([Estimated Date of completion, row above]+[Number of Days Estimated]+[Number of Days Estimated]/7*2),2)=7,1,0)

## Instructions
Project Plan Guide:
•To delete these instructions, select this text box and then hit [Delete].
Date Cells (H6:GU7)
These cells power much of the conditional formatting and allow the project plan to "float." All the cells are indirectly referenced to cell G6, which can be set to a firm date (ex. 2/1/2010) or a reference (ex. =MIN([project dates])). Adjusting cell G6 will shift the entire calendar.
Task Cells (A10:F40)
The tasks have three levels, deliverable, task and sub task. Each has a different conditional format in the Gantt chart area.
Deliverable Sections
The deliverable section(s) (ex. 15:19) can be copied and pasted as rows to add new deliverable sections below the existing sections if needed.
Within each deliverable section you can add additional room for tasks by inserting a row above the light blue row (ex. 13). This way the appropriate conditional formatting is added and no formulas are compromised.
Task s
By entering a task in the B column the conditional formatting will make the associated bar a medium blue. By entering a task in the C column the associated bar will be light blue. The bar is shown via conditional formatting based on the dates entered (Cols D:E) cross referenced with the calendar across the top.
Task dependence/precedence can be managed by creating formulas between the data cells instead of firm dates (ex. =E11+5 vs. 2/10/2010).
Special Events (B2:E7)
Functionality was added to allow for up to five "special events" that will highlight the background color. This was intended for non-task events that may need to be included.
Misc.
- There is a current date indicator that will show the current date on the Gantt chart.
- The Gantt chart bars and the task list will highlight according to % complete status.
- The Page Setup includes repeating rows of 2:9 and repeating columns of A:G. To print a small section of the chart simply select the area of the Gantt chart (ex. H10:AZ41) and set it as the Print Area.
- Hypothetically additional days can be added to the calendar by copy and inserting columns to the left of Column GU. Be sure to check that the formulas in 6:7 and 4:5 have been copied appropriately.